## Annex A.1 Technical Bid
|  | RFP reference number: RFP-DRC-ALT-TUN-2025-004 |  |  |  |  | Annex A.1 Technical Bid
DRC to complete |  |  |  |  | Bidder to complete
# | Line Item | Specification (refer to Annex F - Statement of Works | Quantity required | Line item offered (refer to attached proposal if needed) |  | Country of Origin | Quantity offered
1 | Youth Mapping & Mobilization | Identify and select at least 200 youth across target governorates according to DRC criteria | 200 youth
2 | Soft‑skills & Employability Training | Deliver training modules on communication, teamwork, CV writing, interview techniques, job‑search strategies (using DRC curricula) | 200 youth
3 | Technical / Sector‑specific Training | Deliver sector‑aligned modules (ICT, agriculture, manufacturing, green jobs, tourism) | 200 youth
4 | Pre‑ & Post‑Training Assessments | Conduct and score pre‑ and post‑training tests to measure learning outcomes | 200 assessments pre & 200 post
5 | Private Sector Engagement | Map and secure partnerships with at least 50 companies across key sectors (ICT, agri., manufacturing, green jobs, tourism) | 50 companies
6 | Regional Job Fairs | Plan, organize and execute 4 multi‑sector job fairs (Tunis, Beja, Sahel, Medenine/Gabes); includes venue rental, booths, signage, layout, logistics | 4 fairs
7 | On‑site Workshops & Interviews | Facilitate 4 × regional on‑site workshops (entrepreneurship, employability) and one‑on‑one employer interviews at each fair | 4 fairs
8 | Placement Follow‑Up | Monitor job/internship placements of 200 youth over 3 months using DRC M&E tools; collect employment status, employer feedback
9 | Professional Video Production | Video 1: Testimonial (≈3–5 min); Video 2: Comprehensive overview (≈5–7 min), including editing and rights clearance | 2 videos
10 | High‑Resolution Photography | Capture and edit ≥200 rights‑cleared images across training sessions, fairs, and field activities
11 | Branding & Communication Materials | Design & print signage, banners, brochures, registration forms, name‑tags (per fair)
12 | Progress Reporting | Submit ‑monthly narrative and quantitative reports | 5
13 | Final Project Report | Comprehensive document covering all metrics, success stories, lessons learned, recommendations | 1 report
14 | Project Management & Coordination | Dedicated TEAM
DRC to complete |  |  |  | Bidder to complete
Max. completion time required (days after contract signature): |  | DECEMBER 30th, 2025 |  | Completion time offered (days after contract signature):
Destination (if applicable): |  | Tunisia |  | Destination offered (if applicable):
Minimum bid validity period required: |  | 6 Months |  | Bid validity period offfered:
Additional comments to bidders: |  |  |  | Company Name:
Contact Person:
|  |  |  | Address: |  | Phone number:
|  |  |  | Email Address: |  | Date:
Signed by a duly authorized company representative:
Title:
Print Name:
Stamp of company